## Overview
Data Warehouse Timeline
An overview of timeframe for the project
| Note: | This is a timeline estimation for 2 months since 1st August, 2017
Please note that the time could be changed and expanded during the process
| Data Warehouse |  |  |  | Start Date
| Project Schedule |  |  |  | 2017-08-01
| Project Estimation |  |  |  | 560 hours
| 2017-08-01 | 2017-08-08 | 2017-08-15 | 2017-08-22 | 2017-08-29 | 2017-09-05 | 2017-09-12 | 2017-09-19 | 2017-09-26 | 2017-10-03 | 2017-10-10 | 2017-10-17 | 2017-10-24 | 2017-10-31 | 2017-11-07 | 2017-11-14 | 2017-11-21
| 2017 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3
Project Schedule Diagram
Project Start
Deliverable
Phase 1 & 2
Phase 1, 2
System Design
Project Round 2
Tableau Server
Phase 2 | Deployment at P@K, Brimbank
Kick off
Init setup
Phase 3 | Logical Design
Phase 3 | Installation & Testing
Final Deliverable
Due. June 25
Deliverable
Phase 3
Phase 3 | Deployment
Phase 3 | Deplay at RV, Langton, Linden
Phase 4, 5, 6 | Design & Extraction
Phase 7 | Tableau Server Setup & Testing
Roll out
Finish dev

## Tasks Schedule
Data Warehouse Task Schedule
Autumn Group
| Project Lead: |  |  | Alex Fung
| Project Start Date: |  |  | 2017-08-01 | time axis 2017-07-31 to 2017-10-22
| Display Week: |  |  | 1 |  |  |  |  | 2017-07-31: Week 1; 2017-08-07: Week 2; 2017-08-14: Week 3; 2017-08-21: Week 4; 2017-08-28: Week 5; 2017-09-04: Week 6; 2017-09-11: Week 7; 2017-09-18: Week 8; 2017-09-25: Week 9; 2017-10-02: Week 10; 2017-10-09: Week 11; 2017-10-16: Week 12
[9 empty] | 2017-07-31 | [6 empty] | 2017-08-07 | [6 empty] | 2017-08-14 | [6 empty] | 2017-08-21 | [6 empty] | 2017-08-28 | [6 empty] | 2017-09-04 | [6 empty] | 2017-09-11 | [6 empty] | 2017-09-18 | [6 empty] | 2017-09-25 | [6 empty] | 2017-10-02 | [6 empty] | 2017-10-09 | [6 empty] | 2017-10-16
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Phase 1 | [Name]
1.1 | Install software |  |  | 2017-08-01 | 2017-08-01 | 1 | 100% | 1
1.2 | Setup network, rct |  |  | 2017-08-02 | 2017-08-02 | 1 | 100% | 1
1.3 | Local transfer testing |  |  | 2017-08-03 | 2017-08-03 | 1 | 100% | 1
1.4 | Research SQLServer Edition, Scheduler |  |  | 2017-08-07 | 2017-08-07 | 1 | 100% | 1
1.5 | Design ERD for Lots |  |  | 2017-08-08 | 2017-08-08 | 1 | 80% | 1
1.6 | Design ERD for Fred RMS |  |  | 2017-08-09 | 2017-08-09 | 1 | 80% | 1
1.7 | Design ERD for Fred Dispense |  |  | 2017-08-10 | 2017-08-10 | 1 | 60% | 1
1.8 | Log auditting, xml configuration research |  |  | 2017-08-11 | 2017-08-11 | 1 | 50% | 1
1.9 | Design Metadata_Box |  |  | 2017-08-14 | 2017-08-14 | 1 | 100% | 1
1.10 | Draw ERD, Logical, Physical diagrams, User Guide |  |  | 2017-08-15 | 2017-08-15 | 1 | 100% | 1
1.11 | Design SSIS for Lots |  |  | 2017-08-16 | 2017-08-17 | 2 | 40% | 2
1.12 | Design SSIS for Fred RMS |  |  | 2017-08-21 | 2017-08-22 | 2 | 40% | 2
1.13 | Design SSIS for Fred Dispense |  |  | 2017-08-23 | 2017-08-25 | 3 | 30% | 3
1.14 | Setup trello, and documents |  |  | 2017-08-28 | 2017-08-28 | 0 | 100% | 1
1.15 |  |  |  | Total hours (8 hours/day) |  | 136
2 | Phase 2
2.1 | Design Stage database |  |  | 2017-08-29 | 2017-08-30 | 2 | 0% | 2
2.2 | Design the backup for incident |  |  | 2017-08-30 | 2017-08-31 | 2 | 0% | 2
2.3 | How to investigate if data is not consistent |  |  | 2017-08-31 | 2017-09-01 | 2 | 0% | 2
2.4 | Deploy Stage, schedule backups |  |  | 2017-09-01 | 2017-09-01 | 1 | 0% | 1
2.5 |  |  |  | Total hours (8 hours/day) |  | 56
3 | Phase 3
3.1 | Select relevant tables from Lots |  |  | 2017-09-04 | 2017-09-04 | 1 | 0% | 1
3.2 | Select relevant tables from Fred RMS |  |  | 2017-09-05 | 2017-09-05 | 1 | 0% | 1
3.3 | Select relevant tables from Fred Dispense |  |  | 2017-09-06 | 2017-09-06 | 1 | 0% | 1
3.4 | Select relevant tables from Fred Office |  |  | 2017-09-07 | 2017-09-07 | 1 | 0% | 1
3.5 | Have a consultancy with Hailey for Sales reports |  |  | 2017-09-08 | 2017-09-08 | 1 | 0% | 1
3.6 | Have a consultancy with Hailey for Inventory reports |  |  | 2017-09-11 | 2017-09-11 | 1 | 0% | 1
3.7 | Have a consultancy with Hailey for Customer reports |  |  | 2017-09-12 | 2017-09-12 | 1 | 0% | 1
3.8 | Design Face & Dimension |  |  | 2017-09-13 | 2017-09-14 | 2 | 0% | 2
3.9 | Review Fact & Dimension with Hailey |  |  | 2017-09-14 | 2017-09-14 | 1 | 0% | 1
3.10 | Draw ERD for NDS |  |  | 2017-09-15 | 2017-09-16 | 2 | 0% | 1
3.11 | Build Fact & Dimension |  |  | 2017-09-18 | 2017-09-19 | 2 | 0% | 2
3.12 | Design NDS database |  |  | 2017-09-17 | 2017-09-21 | 5 | 0% | 4
3.13 | Design audtting & backup plan for NDS |  |  | 2017-09-18 | 2017-09-19 | 2 | 0% | 2
3.14 | Review the streaming data at 2 stories |  |  | 2017-09-19 | 2017-09-19 | 1 | 0% | 1
3.15 | Install software for 2 more stories |  |  | 2017-09-20 | 2017-09-20 | 0 | 0% | 1
3.16 | Reivew the the total data, ensure the accuracy |  |  | 2017-09-21 | 2017-09-22 | 2 | 0% | 2
3.17 | Catch-up at the end of rough 1 |  |  | 2017-09-22 | 2017-09-22 | 0 | 0% | 1
3.18 |  |  |  | Total hours (8 hours/day) |  | 176
4 | Phase 4
4.1 | Extract data for Sales DDS (OTC & Script) |  |  | 2017-09-25 | 2017-09-26 | 2 | 0% | 2
4.2 | Convert Tableau using SQL Server as a data source |  |  | 2017-09-26 | 2017-09-26 | 1 | 0% | 1
4.3 | Deploy the sample reports |  |  | 2017-09-27 | 2017-09-27 | 1 | 0% | 1
4.4 | Setup the Tableau Server |  |  | 2017-09-28 | 2017-09-28 | 1 | 0% | 1
4.5 | Configure the server |  |  | 2017-09-29 | 2017-09-29 | 1 | 0% | 1
4.6 |  |  |  | Total hours (8 hours/day) |  | 48
5 | Phase 5
5.1 | Extract data for Membership reports |  |  | 2017-10-02 | 2017-10-03 | 2 | 0% | 2
5.2 | Ask Haikey for a sample customers report |  |  | 2017-10-03 | 2017-10-03 | 1 | 0% | 1
5.3 | Convert Memership reports |  |  | 2017-10-04 | 2017-10-04 | 1 | 0% | 1
5.4 | Upload to Tableau |  |  | 2017-10-05 | 2017-10-05 | 1 | 0% | 1
5.5 | How to schedule daily reports automatically |  |  | 2017-10-06 | 2017-10-06 | 1 | 0% | 1
5.6 |  |  |  | Total hours (8 hours/day) |  | 40
6 | Phase 6
6.1 | Extract data for Inventory reports |  |  | 2017-10-09 | 2017-10-10 | 2 | 0% | 2
6.2 | Catch-up with Nam for Marketing measurement (*) |  |  | 2017-10-10 | 2017-10-10 | 1 | 0% | 1
6.3 | Create a new report |  |  | 2017-10-11 | 2017-10-12 | 2 | 0% | 2
6.4 | Schedule it and verify |  |  | 2017-10-12 | 2017-10-13 | 2 | 0% | 2
6.5 |  |  |  | Total hours (8 hours/day) |  | 56
7 | Phase 7
7.1 | Installation (all stories) |  |  | 2017-10-16 | 2017-10-20 | 5 | 0% | 5
7.2 | Review Boxes, Staging, and NDS |  |  | 2017-10-17 | 2017-10-17 | 1 | 0% | 1
7.3 | Write down the User Guide |  |  | 2017-10-18 | 2017-10-18 | 1 | 0% | 1
7.4 | Review Tableau before rolling out |  |  | 2017-10-19 | 2017-10-19 | 1 | 0% | 1
7.5 | Propose a Membership front-page |  |  | 2017-10-20 | 2017-10-20 | 0 | 0% | 1
7.6 | Catch-up and roll out |  |  | 2017-10-21 | 2017-10-21 | 1 | 0% | 0
7.7 |  |  |  | Total hours (8 hours/day) |  | 72
|  |  |  | Total Project Hours |  | 584
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version includes template rows that allow you to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Checklist
Data Warehouse | [20 empty] | Project Checklist
|  | Start Week | 2017-08-01
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Starting | 2017-08-01 | 2017-08-08 | 2017-08-15 | 2017-08-22 | 2017-08-29 | 2017-09-05 | 2017-09-12 | 2017-09-19 | 2017-09-26 | 2017-10-03 | 2017-10-10 | 2017-10-17 | 2017-10-24 | 2017-10-31 | 2017-11-07 | 2017-11-14 | 2017-11-21 | 2017-11-28 | 2017-12-05 | 2017-12-12 | Notes
| 2017-08-01 | 2017-08-08 | 2017-08-15 | 2017-08-22 | 2017-08-29 | 2017-09-05 | 2017-09-12 | 2017-09-19 | 2017-09-26 | 2017-10-03 | 2017-10-10 | 2017-10-17 | 2017-10-24 | 2017-10-31 | 2017-11-07 | 2017-11-14 | 2017-11-21 | 2017-11-28 | 2017-12-05 | 2017-12-12
Phase
One
Phase
Two
Phase
Three
Phase
Four
Phase
Five